Schedule Of Work

Turner Terrance

January 15t-h-30th Order all Material for Project Ship Electrical boxes for electrician to install

February 1st Install Rack, Recorder, and Main Radio

February 2nd Install Camera and Related equipment 1 and 2

February 3rd Install Camera and Related equipment 3 and 4

February 4th Install Camera and Related equipment 5 and 6

February 5th Install Camera and Related equipment 7 and 8

February 10th Install camera and Related equipment 9 and 10

February 11th Install Camera and Related equipment 11 and 12

February 12th Install Camera and Related equipment 13 and 14

February 15th Install Camera and Related equipment 15 and 16

February 16th Install Camera and Related equipment 17,18,19

Weaver Court

February 22st Install Rack, Recorder, and Main Radio

February 23nd Install Cameras and Related equipment 1 and 2

February 24rd Install Camera and Related equipment 3 and 4

February 25th Install Camera and Related equipment 5 and 6

February 26th Install Camera and Related equipment 7 and 8

March 4th Install Camera and Related equipment 9 and 10

March 5th Install Camera and Related equipment 11,

Tudor Court

March 5th Start installing Rack, Recorder, and Main Radio

March 8th Finish Installing Recorder, Install Camera 1

March 9th Install Camera and Related equipment 2 and 3

March 10th Install Camera and Related equipment 4 and 5

March 11th Install Camera and Related equipment 6,7,8

Meadows

March 12th Install Rack Recorder and Main Radio

March 17th Install Camera and Related equipment 1 and 2

March 18th Install Camera and Related equipment 3 and 4

March 19th Install Camera and Related equipment 5 and 6

March 22nd Install Camera and Related equipment 7 and 8

Rozier Homes

March 23rd Install Rack, Recorder, and Main Radio

March 24th Install Camera and Related equipment 1 and 2

March 25th Install Camera and Related equipment 3 and 4

March 26th Install Camera and Related equipment 5 and 6

March 31st Install Camera and Related equipment 7 Install Rack

April 1st Install Recorder, Main Radio, Camera 1 and Related Equipment

April 2nd Install Camera and Related equipment 2 and 3

April 5th Install Camera and Related equipment 3 and 4

April 6th Install Camera and Related equipment 5 and 6

April 7th-19th Test and check all systems and camera settings for both day and night

April 21st-25th Training

April 28th-30th Training