East Baton Rouge Council on Aging, Inc.

Request for Proposals (RFP)

Master Plan Consulting & Development Services

RFP NO. 03-2018-06

East Baton Rouge Council on Aging, Inc. (EBRCOA)

5790 Florida Blvd.

Baton Rouge, LA 70806

Schedule:

- RFP Issue Date:                              Sunday, June 3, 2018

- Inquiries Due:                                  Friday, June 8, 2018 by 3:00 pm CST

- Clarifications Posted:                       Tuesday, June 12, 2018 by 3:00 pm CST

- Proposals Due:                                Tuesday, June 19, 2018 by 3:00 pm CST

- Short Listing                                     Thursday, June 20, 2018

- Evaluation Interviews                      June 21-22, 2018

- Notice of Award                               June 26, 2018

- Anticipated Contract Date:              July 2, 2018

- Preliminary Kick-Off Meeting          July 9, 2018

- 35% Plan Completion for Review    July 31, 2018

- 65% Plan Completion for Review    August 17, 2018

- 95% Plan Completion for Review    September 14, 2018

- Plan Presentation to Agency           October 1, 2018

Register: https://ha.economicengine.com/requests.html?company_id=60574

Submission Deadline: 3:00 PM, June 15th, 2018

Request To: Architecture, Engineering, Management Consulting Firms

Table of Contents

1.	Overview 	3

2.	Scope of Work	3

3.	Request for Proposals	4

3.1	Inquiries	4

3.2	Proposal Review Committee	4

3.3	Review and Selection	4

3.4	Licensing & Insurance	4

4.	Reservation of Rights	5

5.	Evaluation Criteria	6

6.	Submission Requirements	7

7.	Conflict of Interest	7

8.	Award / Compensation	7

# Overview

- The East Baton Rouge Council on Aging (Agency), is issuing this Request for Proposals (RFP) to solicit responses from qualified Consultant Teams/Firm(s) to facilitate the development of a Master Aging Plan (MAP) for the Council. The plan is intended to transform the Parish of East Baton Rouge into an Age-Friendly Community (AFC); a place where structures and services are adapted to be accessible to and inclusive of older adults with varying needs and capacities, a community that will enable older adults to live in a secure environment, enjoy good health, and continue to participate fully in the community. The (MAP) will also serve as a guide for sustainability, and for the expansion of services and facilities. The firm selected for this project will have expertise in a minimum of four (4) or more of the following disciplines: urban planning, zoning and form base codes, land use planning, strategic planning, urban design, market analyses, landscape architecture, transportation planning, site planning, and project planning and management. The (MAP) will be a living document that will serve as a blueprint for ongoing community building and collaborative planning by the Council, its partners, and the community at large.

- With an eye toward expanding its role in providing affordable housing and increased programmatic services for Baton Rouge’s growing senior population, the East Baton Rouge Council on Aging desires to be a leader in the contemporary transformation of providing wrap-around services for its seniors. The Master Aging Plan will be comprehensive in scope, incorporating elements of land use, zoning, urban design, parking, facility and strategic planning into a coordinated vision and implementation program that will identify short, medium, and long-term projects/plans for public-private partnerships and investment, for the next 10-20 years. The plan will be guided by a detailed market analysis that will examine current and future local aging and community trends, and will establish future needs and market (services) demand. The plan will also address potential new redevelopment or expansion areas. The Agency’s overarching goal with this plan is to provide a framework to align its financial, programmatic, and operational resources to best deliver higher, increased, and more easily accessible services to its clients.

# Scope of Work (SOW):

The services provided by the selected consulting team/firm shall perform the following work in conjunction with the Agency’s ‘Master Plan Committee’ which will include representatives of the Agency’s administrative areas. The collaborative effort will assess current utilization and future space and organizational needs, programmatic needs, and demographics of growth. The Master Aging Plan will be a living document to serve as a blueprint for ongoing community relationship building and collaborative planning by the Agency, its partners, other levels of local and state government, businesses, and the community at large, and shall address the following key components:

- Vision for next 20 years, with specifics on the next 10 years.

- Highlight the mission, immediate (0-11 months), short-term (1-5yrs), medium-term (6-10yrs), and long-term (11-20yrs) goals of agency.

- Plan for the improvement and utilization of existing (owned) facilities.

- Plan for addressing workforce needs through space realignment, reconfiguration, and site expansion.

- Discussion of the integration of sustainable development and expansion goals, energy benchmarking and efficiency plan at existing-owned sites.

- Incremental plans to modernize or update program efficiency and effectiveness.

- Development of a financial sustainability plan, with efforts defined in detail.

- Plan for the development of collaborative public-private partnerships.

- Development of immediate, mid-term, and long-term demographics with trend analysis, along with economic indicators on the last 5 years of growth in the city’s aging population.

- Development of a single-point access strategy for health care access to seniors.

- Plan for the development of a Senior Village single site housing complex for older adults.

- Consultant shall provide a 35%, 50%, and a 95% phase-term completion document for review and comment.

- Development of a plan to expand availability of safe and accessible transportation.

- Development of a plan to provide innovative housing options that allow for progressive care and aging in-place services for clients.

- Development of a plan to expand and enhance health care services for seniors, to strengthen social and recreational options, and improvement of accessibility of outdoor spaces within the Eco-Village.

- Development of a sustainability model that coincides with the MAP’s 10-year and 20-year plan component.

- Development of a plan to expand the life-long learning opportunities, along with addressing the mental health needs of seniors.

# Request for Proposals

## Solicitation Inquiry

All inquiries related to this RFP are to be directed in writing to the e-procurement website address located on the front cover of this RFP packet.

## Qualifications Review

Award factors will be utilized by the Agency’s evaluation committee, which shall consist of a three (3) person committee, appointed by the Agency head.

## Review and Selection

Responses will be evaluated by the Agency based on the experience and demonstrated capacity of the consultant to meet the needs of the Agency. The EBRCOA reserves the right to conduct a “Best and Final” Negotiation with the top-ranked and scored firm.  The following criteria will be taken into account in evaluating responses:

- Experience and qualifications of team

- Examples of prior similar work

- Approach / Methodology

- Cost / Fees

## Fees

- Hourly Rate: (Include a total for all personnel costs, listing individual rates per team member.)

- Fixed Fee: (Lump sum fee for services, which shall include all personnel costs associated with this project.)

## Licensing and Insurance Requirements

Without limiting or diminishing the Proposer’s obligation to indemnify or hold the Agency harmless, Proposer shall procure and maintain or cause to be maintained, at its sole cost and expense, the following insurance coverages during the term of this Contract.

- Commercial General Liability: Policy’s limit of Liability shall not be less than $1,000,000 per occurrence;

- Professional Liability: Proposer shall maintain Professional Liability Insurance providing coverage for the Proposer’s performance of work included within this contract, with a limit of liability of not less than $1,000,000 per occurrence and $2,000,000 annual aggregate.

- General Insurance Provisions (All Lines): Any insurance carrier providing insurance coverage hereunder shall be admitted to the State of Louisiana and have an A-M BEST rating of not less than an A, unless such requirements are waived, in writing, by the Risk Manager for the City of Baton Rouge.  If the City’s Risk Manager waives a requirement for a particular insurer, such waiver is only valid for that specific insurer, and only for one (1) policy term. Proposer shall cause Proposer’s insurance carrier(s) to furnish the EBRCOA with a properly executed original Certificate of Insurance, and certified original copies of Endorsements effecting coverage.  Proposer shall not commence operations until the EBRCOA has been furnished original Certificate(s) of Insurance, and certified original copies of endorsements.

- Proposer shall pass down the insurance obligations contained herein to all tiers of sub-contractors working under this contract.

- Proposer agrees to notify the EBRCOA immediately or within 2 business days, of any and all claims by a 3rd party or any incident or event that may give rise to a claim arising from the performance of this contract.

- A copy of the proposer’s business/occupational license allowing that entity to provide such services within the Parish of East Baton Rouge, and/or State of Louisiana.

- A copy of the proposer’s license(s) or certification(s) issued by the State of Louisiana licensing authority, allowing the proposer to provide such services.

NOTE: Consultant shall name the EBRCOA as “Additionally Insured” on all above policies.

# EBRCOA’s Reservation of Rights

- Right to Reject, Waive, or Terminate the RFP; the Agency reserves the right to reject any or all proposals, to waive any formality in the RFP process, or to terminate the RFP process at any time, if deemed by the EBRCOA to be in its best interests;

- Right to Not Award; the Agency reserves the right not to award a contract pursuant to this RFP;

- Right to Solicit Additional RFPs; the Agency reserves the right to pursue additional RFQ’s for stand-alone projects or specialty projects, if deemed by the Agency to be in its best interests.

- Right to Terminate; The Agency reserves the right to terminate a contract awarded pursuant to this RFP, at any time, for any reason, for no reason, or for its convenience upon five (5) days written notice to the successful proposer(s).

- Right to Determine Time and Location; The Agency reserves the right to determine the days, hours, and locations that the successful proposer(s) shall provide the services called for in this RFP;

- Right to Determine Financial Responsibility and Viability; the Agency reserves the right to require of proposer information regarding financial responsibility and viability of such other information as the Agency determines is necessary to ascertain whether a proposal is in fact the lowest responsive and responsible proposal submitted.

- Right to Retain Proposals; the Agency reserves the right to retain all proposals submitted and not permit withdrawal for a period of sixty (60) days subsequent to the deadline for receiving proposals without the written consent of the agency’s Contracting Officer (CO).

- Right to Negotiate Fees; the Agency reserves the right to negotiate the fees proposed by the proposer entity;

- Right to Reject Any Proposal; the Agency reserves the right to reject and not consider any proposal that does not meet the minimum requirements of this RFP, including but not necessarily limited to incomplete proposals and/or proposals offering alternate or non-requested services;

- No Obligation to Compensate; the Agency shall have no obligation to compensate any proposer for any costs incurred in responding to this RFP;

- Right to Prohibit; the Agency shall reserve the right to at any time during the RFP process or subsequent contract process, to prohibit any further participation by a proposer or reject any proposal submitted that does not conform to any of the requirements detailed herein.

# Evaluation Criteria

Award factors will be utilized by the Agency’s evaluation committee, which shall consist of a three (3) person committee.  Award of points for each listed factor will be based upon the documentation that the proposer submits within his/her proposal submittal as detailed within this section.  Each proposal received will first be evaluated for responsiveness (e.g., meets the minimum of the published requirements.) Criteria, as listed in Section 3.3 to be used to evaluate the RFP responses will include, but not be limited to the following:

- Experience and qualifications of team

- Examples of prior similar work

- Approach / Methodology

- Cost / Fees

To enable the EBRCOA to efficiently evaluate the responses, it is important that the respondents follow the required format in preparing their responses. Responses that do not conform to the prescribed format shall not be evaluated. Pages shall be no larger than letter size (8 ½” by 11”); each section shall be separated by a tabbed divider within all binders.

CONTENT OF PROPOSAL:

Each response shall be submitted as outlined in this section. Please include an outside cover and first page, containing the name of the project. A table of contents should be next, followed by dividers separating each of the following sections:

Divider #1: Firm Information

- Firm name; address; contact telephone numbers for all firm locations.

- Legal Structure of firm, i.e., sole proprietorship, partnership, corporation, and size of firm.

- Number of years’ firm has been in business.

- Name of principals in firm.

- Primary contact.

- Organizational description.

- Description of firm’s philosophy.

Divider #2: General Company History/Qualifications

- A brief history of the Principal Consultant and the services routinely provided.

- An organizational chart that explains team member responsibilities.

- Name of the project team leader that will be in charge of the project, if not the Principal Consultant.

- Resumes of all persons to be assigned to the project, with their prospective roles identified.

Divider #3: Experience & References

Submittals:  One (1) original and three (3) bounded copies to be included within four (4) white 1-inch binders, and a thumb drive with an electronic coy of the proposal in pdf format, are to be delivered to the EBRCOA Administrative Facility, at the address set forth below, at or before 3:00 pm CST on Friday, June 15th, 2018.  Submittal packets are to be labelled: RFP Master Plan Consulting & Development Services 16-2018-05.

East Baton Rouge Council on Aging

5790 Florida Blvd.

Baton Rouge, LA 70806

# Submission Requirements

A copy of the RFQ package in its entirety, including the scope of work is available for review and/or download from the EBRCOA website’s solicitation section, or by registering your company at economicengine.com, and then reviewing the solicitations section.

- A Profile of Firm Form (See attachment)

- Proposal

- A statement of interest

- A detailed summation outlining the respondent’s experience, the experience of key team members and a response to the qualification review criteria

- A fee proposal for services (See Appendix-A sample) Use Fee #1 category

- Bidders Statement of Non-Collusion (See attachment)

- List of current and past clients

- W-9 Form (See attachment)

# Conflict of Interest

Proposers shall be required to acknowledge by signature, and submit with their proposals, a “Bidders Statement of Non-Collusion” form, included in proposal packet.  Failure to include this signed form in the submitted proposal packet shall deem the proposer non-responsive, and proposals shall be returned with the proposer being disqualified.  As required, the EBRCOA shall comply with Public Bid Law (R.S. 38:2212.7).

# Contract Award / Service Standards / Compensation

# It is the responsibility of the successful proposer(s) to ensure that all work performed pursuant to this RFP shall conform and comply with all applicable local, state, and federal codes, statutes, regulations, and laws.  Compensation shall only be made when the project is completed in full.